## Slide 1
Monday | Tuesday | Wednesday | Thursday | Friday
 |  | 1 | 2 | 3
6 | 7 | 8 | 9 | 10
13 | 14 | 15 | 16 | 17
20 | 21 | 22 | 23 | 24
27 | 28 | 29 | 30 | 
As of: 04.30.26
Review the activities and dates on this calendar to facilitate the transition from TeamWorks to GA@WORK. Send any questions to nextgen@sao.ga.gov.
Get to Go-Live Calendar: Finance & Procurement
April 2026
FDM VALIDATION FOR GOLD BUILD
FDM VALIDATION FOR GOLD BUILD
BUDGET: AGENCY READINESS – TRAINING / FY27 FILE PREPARATION
BUDGET: AGENCY READINESS – TRAINING / FY27 FILE PREPARATION
BUDGET: AGENCY READINESS – TRAINING / FY27 FILE PREPARATION
BUDGET: AGENCY READINESS – TRAINING / FY27 FILE PREPARATION
BUDGET: AGENCY READINESS – TRAINING / FY27 FILE PREPARATION
ADAPTIVE: FUTURE BUDGET BUILD SIMULATION
ADAPTIVE: FUTURE BUDGET BUILD SIMULATION
KEY
Acct. Payable
Supplier Acct.
Adaptive
FDM
Budget
Grants
Banking
Expenses
PRO
General FIN
Bus. Assets
Projects
ADAPTIVE: FUTURE BUDGET BUILD SIMULATION
ADAPTIVE: FUTURE BUDGET BUILD SIMULATION
ADAPTIVE: FUTURE BUDGET BUILD SIMULATION

## Slide 2
Get to Go-Live Calendar: Additional Task Detail
Task / Activity | Impacted Business Area | Date/Timeframe | Final Due Date
Budget: Agency Readiness – Training / FY27 File Preparation During this time, budget development training will take place to teach budget employees how to create the FY27 Budget Workbook or EIB file based on the tentatively approved budget. | Budget Roles | March 2 – May 13 | May 13
Adaptive Planning: Future Budget Build Simulation Agency participants complete Future Budget Build Simulation activities for Adaptive. Agencies will be invited to specific sessions during this time frame. All participation will conclude May 15. | Adaptive Planning / Budget Roles | March 16 – May 15 | May 15
FDM Validation for GOLD Build Review FDM Crosswalk for all agency specific Worktags. | Finance Roles | April 20 – May 1 | May 1
April 2026

## Slide 3
SUNDAY | Monday | Tuesday | Wednesday | Thursday | Friday | SATURDAY
 |  |  |  |  | 1 | 2
3 | 4 | 5 | 6 | 7 | 8 | 9
10 | 11 | 12 | 13 | 14 | 15 | 16
17 | 18 | 19 | 20 | 21 | 22 | 23
24 | 25 STATE HOLIDAY | 26 | 27 | 28 | 29 | 30
BUDGET: AGENCY READINESS – TRAINING / FY27 FILE PREPARATION
FDM VALIDATION FOR GOLD BUILD
ADAPTIVE: FUTURE BUDGET BUILD SIMULATION
BUDGET: AGENCY READINESS – TRAINING / FY27 FILE PREPARATION
FDM VALIDATION FOR CATCH UP
ADAPTIVE: FUTURE BUDGET BUILD SIMULATION
BUDGET: AGENCY READINESS TRAINING / FY27 FILE PREP
FDM VALIDATION FOR CATCH UP
ADAPTIVE: FUTURE BUDGET BUILD SIMULATION
FY27 BUDGET SUBMISSION DUE
FDM VALIDATION FOR CATCH UP
FDM VALIDATION FOR CATCH UP
May 2026
Procurement:
Final day for sourcing events to be under evaluation for go-live
Procurement:
Jaggaer catalog pricing updates
Get to Go-Live Calendar: Finance & Procurement
Supplier Accounts:
TeamWorks Supplier/ Customer entry deadline
FDM:
Worktag change submission deadline
Budget:
FY27 Budget Submission Review
BUDGET: FY27 BUDGET SUBMISSION REVIEW
BUDGET: FY27 BUDGET SUBMISSION REVIEW
Procurement:
FY27 Contract Renewals for Contract Management
Banking:
Validate bank accounts
KEY
Acct. Payable
Supplier Acct.
Adaptive
FDM
Budget
Grants
Banking
Expenses
PRO
General FIN
Bus. Assets
Projects
FDM VALIDATION FOR CATCH UP
P-Card:
April 27 statements due
P-Card:
Admins need to make sure all P-Card holder IDs are in Bank of America Works and are accurate

## Slide 4
Get to Go-Live Calendar: Additional Task Detail
Task / Activity | Impacted Business Area | Date/ Timeframe | Final Due Date
Tasks / Activities highlighted in red are “Hard Freeze Dates”. These dates indicate the final day to complete the task or activity in TeamWorks before the transition to GA@WORK on July 1. |  |  | 
Budget: Agency Readiness – Training / FY27 File Preparation During this time, budget development training will take place to teach budget employees how to create the FY27 Budget Workbook or EIB file based on the tentatively approved budget. | Budget Roles | March 2 – May 13 | May 13
Adaptive Planning: Future Budget Build Simulation Agency participants complete Future Budget Build Simulation activities for Adaptive. Agencies will be invited to specific sessions during this time frame. All participation will conclude May 15. | Adaptive Planning / Budget Roles | March 16 - May 15 | May 15
FDM Validation for GOLD Build Review FDM Crosswalk for all agency specific Worktags. | Finance Roles | April 20 – May 1 | May 1
FDM Validation for Catch Up Review FDM and submit any updates to be included prior to soft open. | Finance Roles | May 2 - June 12 | June 12
Sourcing Events Sourcing events (RFP, RFQ, RFQC, RFI) to be under evaluation by May 4th for Go-Live | Sourcing Event Buyers/ APO Roles | May 4 | May 4
Validate GA@WORK Bank Accounts Agencies validate bank accounts being set up in GA@WORK | Banking Roles | May 11 | May 11
FY27 Budget Submission Due Date Submit your agency FY27 budget for review by SAO and OPB. | Budget Roles | May 15 | May 15
FY27 Budget Submission Review OPB reviews agency submitted FY27 Annual Operating Budget (AOB) | Budget Roles | May 15 – June 12 | June 12
Hard Freeze: Supplier and Customer Accounts in TeamWorks Final day for agencies to request adds or edits for the following in TeamWorks: Suppliers (including Federal and HR Suppliers) Customers (including Federal Customers) | Supplier Liaison Roles | May 19 | May 19
Monthly P-Card Statements Due May 27 P-Card statements are due for payment | P-Card Holders / Admins / Accounts Payable | May 21 | May 21
FDM Worktag Change Submission Deadline Any additions/changes to agency-specific FDM Worktags made since May 1 that would impact employee coding need to be submitted to NextGen_FDM@sao.ga.gov | Finance Roles | May 22 | May 22
Hard Freeze: Jaggaer Catalog Pricing Updates Suppliers must update Catalog Pricing and Contract Managers must Approve in Jaggaer prior to switching UIT to Production | Procurement Roles | May 27 | May 27
FY27 Contract Renewals for Contract Management Complete all FY27 contract renewals by May 29 to support the June 6 snapshot | Procurement Roles | May 29 | May 29
May 2026

## Slide 5
 | Monday | Tuesday | Wednesday | Thursday | Friday | SATURDAY
 | 1 | 2 | 3 | 4 | 5 | 6
7 | 8 | 9 | 10 | 11 | 12 | 13
14 | 15 | 16 | 17 | 18 | 19 | 20
21 | 22 | 23 | 24 | 25 | 26 | 27
28 | 29 | 30 |  |  |  | 
Get to Go-Live Calendar: Finance & Procurement
June 2026
SOFT LAUNCH
SOFT LAUNCH
Grants:
Post-Freeze Grant Exception Recording
Expenses:
FY26 Cash Advances and Expenses Approvals Due
Expenses:
Concur Back Office Approvals Due
FDM VALIDATION FOR CATCH UP
FDM VALIDATION FOR CATCH UP
Grants: Validate Awards/Billing Schedule
ADAPTIVE: Confirm roster of users
CONCUR OFFLINE
Adaptive:
Budget Build Sign Off
Procurement:
Jaggaer Sourcing Director
FDM: NEW FY27 FDM WORKTAGS
FDM: NEW FY27 FDM WORKTAGS
BUDGET: FY27 BUDGET SUBMISSION REVIEW
BUDGET: FY27 BUDGET SUBMISSION REVIEW
GRANTS: CATCHUP ACTIVITIES
Expenses:
FY26 Cash Advances and Expense Reports Due in Concur
Adaptive:
Confirm roster of users
GRANTS: CACTHUP ACTIVITIES
GRANTS: SPONSOR CHANGES
Procurement:
Vendor Self-Registration Deadline for Non-GDOT Employees
Supplier Accounts:
Final day for Supplier Access
KEY
Acct. Payable
Supplier Acct.
Adaptive
FDM
Budget
Grants
Banking
Expenses
PRO
General FIN
Bus. Assets
Projects
PROVIDE COSTING ALLOCATION DATA FILES
FDM:
Select Worktags frozen
Procurement:
Clean Up Old or Outstanding
PO & Receipts
FDM:
Freeze Locations
Grants:
Provide Awards/ Billing Schedules
Procurement:
eProcurement Catalog PO Sourcing deadline
PROVIDE COSTING ALLOCATION DATA FILES
P-Card:
May 27 statements due
P-Card:
Admins need to make sure all P-Card holder IDs are in Bank of America Works and are accurate
P-Card:
Final P-Card statement in PeopleSoft/ TeamWorks for statements on the 15th
P-Card:
Final P-Card statement in PeopleSoft/ TeamWorks for statements on the 27th

## Slide 6
Get to Go-Live Calendar: Additional Task Detail
Task / Activity | Impacted Business Area | Date/Timeframe | Final Due Date
FDM Validation for Catch Up Review FDM and submit any updates to be included prior to soft open. | Finance Roles | May 2 - June 12 | June 12
FY27 Budget Submission Review OPB reviews agency submitted FY27 Annual Operating Budget (AOB) | Budget Roles | May 15 – June 12 | June 12
Provide Costing Allocation Data Files Agencies to provide their agency costing allocation data files by June 12 | Financial Accounting | June 1 – June 12 | June 12
Hard Freeze: FDM Companies, Ledger Accounts, Book Code Final day for agencies to request adds or edits to TeamWorks business units or accounts, as the following GA@WORK worktags will be frozen. Book Code TeamWorks Business Unit: GA@WORK Company / company hierarchy TeamWorks Accounts: Ledger Account / Ledger Account Summaries Revenue Category / Revenue Category Hierarchy Spend Category / Spend Category Hierarchy | Foundation Data Model | June 3 | June 3
Hard Freeze: Procurement Cutoff date of Supplier Access to make changes via Supplier Self Service Portal Cutoff date for eProcurement Catalog Purchase Orders (POs) that need to be sourced by go-live (July 1). In preparation for the transition to GA@WORK Marketplace, all Punchout and Hosted catalogs' orders will need to be dispatched by close of business on June 5, 2026. Beginning June 6, the connection between PeopleSoft and GA Virtual Catalogs will be disconnected. | Procurement Roles | June 5 | June 5
Clean Up Old or Outstanding POs & Receipts All clean up of old or outstanding POs should be completed by June 5 so contracts can be converted starting June 6 | Procurement Roles | June 5 | June 5
Provide Awards/Billing Schedules Submit awards and billing schedule files for loading and validation to support accurate grant setup and invoicing. | Grants Roles | June 5 | June 5
Hard Freeze: Supplier Management Freeze of Supplier Access to Make Changes via Jaggaer Supplier Self Service Portal; Freeze of New Bidders | Suppliers/ Bidder Roles | June 5 | June 5
Hard Freeze: FDM Locations | Foundation Data Model | June 6 | June 6
Validate Awards/Billing Schedules Review loaded awards and billing schedules to confirm completeness, accuracy, and alignment with source documentation. | Grants Roles | June 14 - 16 | June 16
Adaptive Planning Budget Build Simulation Sign-off Complete sign-off process for Adaptive Future Budget simulation testing | Enterprise Budget Office roles | June 15 | June 15
June 2026 (Page 1 of 2)

## Slide 7
Get to Go-Live Calendar: Additional Task Detail
Task / Activity | Impacted Business Area | Date/ Timeframe | Final Due Date
Final P-Card Statements in PeopleSoft/TeamWorks Final day for P-Card final statements in PeopleSoft/TeamWorks for statement dates on the 15th of the month | P-Card Holders / Admins / Accounts Payable | June 15 | June 15
Monthly P-Card Statements Due May 27 P-Card statements are due for payment | P-Card Holders / Admins / Accounts Payable | June 21 | June 21
New Employee Vendor Self-Registration (Non-GDOT Employees) Final date for non-GDOT employees to self-register as vendors in TeamWorks. If a new employee is not registered by this date, they will not be able to receive travel reimbursement until after GA@WORK go-live. | Employees that need to register as vendors | June 22 | June 22
Post-Freeze Grant Worktags Exception Recording Manually record any exception handling grant worktags created after freeze date (note: this is for with a high volume that would be loaded via EIB) | Grants Roles | June 22 | June 22
Grants Catchup Activities Create Catchup in GA@WORK: Awards, Award Schedules, Billing Schedules, and Sponsors | Agency Grants Management Roles | June 22- 30 | June 30
GA@WORK Soft Launch On a limited basis, agencies will be granted the ability to make updates in GA@WORK in preparation for go-live. Access will be restricted to only necessary roles. HR and Payroll partners will complete catch-up transactions during this time. | Finance/HCM Roles | June 22- 30 | June 30
Jaggaer Sourcing Director Close date of all events in Jaggaer Sourcing Director for USG and GTA | Procurement Roles at USG and GTA | June 24 | June 24
FY26 Travel and Expense Reports Due in Concur Final day for employees to submit expenses in Concur | All Employees | June 24 | June 24
FY26 Expense Approvals Due in Concur Last day for manager to approve employee travel expenses in Concur. Any travel expenses not submitted by June 24 and approved by June 26 will have to be processed outside of Concur until June 30. | Expense Approvers | June 26 | June 26
Adaptive: Confirm Roster of Users Confirm the roster for those who will require Adaptive Planning access. Agencies that will be implementing Adaptive Planning will need to validate their list of users that will require access by July 13. | Agency Budget Office Personnel Roles | June 26 – July 13 | July 13
Final P-Card Statements in PeopleSoft/TeamWorks Final day for P-Card final statements in PeopleSoft/TeamWorks for statement dates on the 27th of the month | P-Card Holders / Admins / Accounts Payable | June 27 | June 27
Back Office Approvals Due in Concur Final day for back-office approvals to be submitted in Concur. | Back Office Travel Administrators | June 29 | June 29
Grants Sponsor Changes Request New Sponsors and Sponsor Changes as needed via Support Portal | Agency Grants Management Roles | June 29 – Going forward | --
Concur Offline Concur will be unavailable for all bookings and expenses. (State travel agent can be used as necessary) | All Employees | June 30 | June 30
June 2026 (Page 2 of 2)

## Slide 8
Monday | Tuesday | Wednesday | Thursday | Friday | 
 |  | 1 | 2 | 3 STATE HOLIDAY | 4
6 | 7 | 8 | 9 | 10 | 11
GRANTS: SPONSOR CHANGES
Go-Live Calendar: Finance & Procurement
July 2026
Business Assets:
Creation of new assets in TeamWorks;
Dispose assets;
Transfer assets
Expenses:
Concur open for FY27 travel
ONLY PERIOD 12 WILL BE OPEN IN TEAMWORKS
ADAPTIVE: CONFIRM ROSTER OF USERS
FY26 PAYMENTS MADE IN TEAMWORKS JULY 1 -10
FY26 PAYMENTS MADE IN TEAMWORKS JULY 1 -10
Banking:
Provide Ending Bank Balance as of June 30
GO-LIVE!
Procurement:
Start Entering FY27 POs & Applicable Payments in GA@WORK
FDM: NEW FY27 FDM WORKTAGS
Banking:
Settlement Initiation
Banking:
Start recording bank statements
FDM: NEW FY27 FDM WORKTAGS
GRANTS: CREATE NEW SPONSOR INVOICES
GRANTS: CREATE NEW SPONSOR INVOICES
Expenses:
Final supplier invoices for company paid rental cars, hotel, and airfare
Accounts Payable:
Final submission & payment of voucher uploads from agency 3rd party systems
PERIOD 12 CLOSES: CLOSE FY26 IN TEAMWORKS
KEY
Acct. Payable
Supplier Acct.
Adaptive
FDM
Budget
Grants
Banking
Expenses
PRO
General FIN
Bus. Assets
Projects
ADAPTIVE: CONFIRM ROSTER OF USERS
PAYMENT OF ALIGHT JULY VOUCHER IN TEAMWORKS
PAYMENT OF ALIGHT JULY VOUCHER IN TEAMWORKS
REVIEW COSTING ALLOCATIONS
REVIEW COSTING ALLOCATIONS
Projects:
Freeze of capitalization of CIP costs and registering from a project asset
P-Card:
Final P-Card statement in PeopleSoft/ TeamWorks for statements on the 4th

## Slide 9
Monday | Tuesday | Wednesday | Thursday | Friday
13 | 14 | 15 | 16 | 17
20 | 21 | 22 | 23 | 24
27 | 28 | 29 | 30 | 31
Go-Live Calendar: Finance & Procurement
July 2026 (cont.)
ADAPTIVE:
CONFIRM ROSTER OF USERS
SHARE OUTSTANDING CHECKS INFORMATION WITH BANKS
SHARE OUTSTANDING CHECKS INFORMATION WITH BANKS
PROVIDE OUTSTANDING PAYMENTS FROM TEAMWORKS
Grants:
Provide Converted Grants Billing & AR Amounts
GRANTS: CREATE NEW SPONSOR INVOICES
GRANTS: CREATE NEW SPONSOR INVOICES
GRANTS: CREATE NEW SPONSOR INVOICES
KEY
Acct. Payable
Supplier Acct.
Adaptive
FDM
Budget
Grants
Banking
Expenses
PRO
General FIN
Bus. Assets
Projects
FDM: NEW FY27 FDM WORKTAGS
Banking:
Settle 3rd party payments
FDM: NEW FY27 FDM WORKTAGS
FDM: NEW FY27 FDM WORKTAGS
Adaptive:
Soft Go-live
PERIOD 998 CLOSEOUT (LATE CLOSE AGENCIES)
Accounts Payable:
In period 12/FY26: TeamWorks, record a journal entry to Debit Cash / Credit Accounts Payable for payments made between July 1 -10
Accounts Payable:
Agencies to confirm July payment in Alight system
PERIOD 998 CLOSEOUT (EARLY CLOSE AGENCIES)
Accounts Payable:
In period 1, FY27: GA@WORK, record Ad Hoc Payments made between July 1 – 10, by July 31
Banking:
Settle 3rd party payments
TEAMWORKS FINANCE DATA AVAILABLE IN GA@WORK

## Slide 10
Go-Live Calendar: Additional Task Detail
Task / Activity | Impacted Business Area | Date/Timeframe | Final Due Date
GA@WORK Go-live! GA@WORK is open for all end users | All Employees | July 1 | --
New FY27 FDM Worktags Any new FY27 FDM Worktags to be requested via the Support Portal starting on July 1, 2026. If FY27 worktags are needed for FY27 budget or other reasons prior to July 1, email Nextgen_FDM@sao.ga.gov | Finance Roles | July 1 and going forward | --
Grants Sponsor Changes Request New Sponsors and Sponsor Change as needed via Support Portal | Agency Grants Management Roles | June 29 and going forward | --
Grants Sponsor Invoices Create New Sponsor Invoices in GA@WORK (only for Agencies not using LTD process) | Agency Grants Management Roles | July 1 and going forward | --
GA@WORK Settlement Initiation Agencies start settlements in GA@WORK (including off-cycle payroll settlements). Note: SAO will release on-cycle employee payroll payments in GA@WORK. | Settlement Specialist Roles | July 1 | July 1
Concur Online Concur is open for booking and submitted FY27 travel expenses only. | All Employees | July 1 | --
Start Entering FY27 POs and Applicable Payments in GA@WORK Enter FY27 purchase orders (POs) in GA@WORK and process eligible payments for items not tied to a prior-year PO. This includes direct pay transactions and payments for an FY27 PO entered in GA@WORK. | Procurement and Accounts Payable Roles | July 1 | --
Review Costing Allocations Agencies to review Cost Allocations in GA@WORK to validate before first payroll run in GA@WORK | Financial Accounting | July 1 – 8 | July 8
Payment of Alight July voucher in TeamWorks Agencies to change the date on the July Alight voucher (June activity) to make the payment on July 9th and enter business unit number and name into the memo field. (Note: SAO will do this for agencies on PYSS). Also, ensure last check run in TeamWorks is set to pick up all vouchers available through July 10th. | Accounts Payable | July 1 – 9 | July 9
FY26 Payments made in TeamWorks July 1 -10 For FY26 payments made in Period 12 in TeamWorks between July 1–10, two action items are required: In period 12/FY26: TeamWorks, record a journal entry to Debit Cash / Credit Accounts Payable by July 17 In period 1, FY27: GA@WORK, record Ad Hoc Payments for TeamWorks payments made between July 1 – 10, by July 31 | Finance/ Accounts Payable Roles | TeamWorks MANJV: July 17 GA@WORK Ad Hoc Payment: July 31 | July 17 July 31
Provide Ending Bank Balance as of June 30 Provide each bank account’s June 30, 2026, balance (submit via KiteWorks) | Banking Roles | July 3 | July 3
Final P-Card Statements in PeopleSoft/TeamWorks Final day for P-Card final statements in PeopleSoft/TeamWorks for statement dates on the 4th of the month | P-Card Holders / Admins / Accounts Payable | July 4 | July 4
July 2026 (Page 1 of 4)

## Slide 11
Go-Live Calendar: Additional Task Detail
Task / Activity | Impacted Business Area | Date/ Timeline | Final Due Date
Start Recording Bank Statements Bank statements start to be loaded into GA@WORK via integration for Agencies to begin using bank reconciliation functionality. | Banking Roles | July 8 | July 8
Supplier Invoices Process final FY26 supplier invoices for company paid: Rental cars, hotels, and airfare for payment in TeamWorks | Expenses | July 8 | July 8
Hard Freeze: Projects Freeze of capitalization of CIP costs and registering from a project asset | Projects | July 9 | July 9
Hard Freeze: Business Assets The following need to be completed in TeamWorks: Manually registered assets (Express add) Disposals Assets registered in TeamWorks through an AP/PO need to be fully processed Transfer assets in TeamWorks (as required) | Business Assets | July 9 | July 9
Hard Freeze: Vouchers and Invoices 3rd Party Systems Final submission & payment of voucher uploads from agency 3rd party systems into TeamWorks (refer to your Agency specific timeline as well) | Accounts Payable | July 9 | July 9
FY26 Period 12 Closes in TeamWorks – Final Day for all TeamWorks activity except MANJVs For all business areas, Agencies will have full access to TeamWorks modules to perform Period 12 closeout until 7 p.m. on July 10, 2026. July 10 is the final day for any payments or transactions to be made in TeamWorks. The following is a list of activities that must be completed by July 10 in TeamWorks. Expenses Final settlement of cash advances from Concur Final settlement of expense reports from Concur Agencies’ final payments for company paid vouchers Accounts Payable/Accounts Receivable Agencies will need to prepare all invoices for final settlement Submission and payment of voucher uploads from agency third party systems to TeamWorks Submit/approve invoice adjustments for GL posting corrections in TeamWorks Submit/approve supplier refunds in TeamWorks Create vouchers for all receipts for PO-related invoices Settle approved supplier invoices (vouchers) in TeamWorks Complete $0 invoices or adjustments in TeamWorks Complete supplier refunds (credit) in TeamWorks Final submission and payment of voucher uploads for HR payments Stop entry of all customer account transactions in TeamWorks Final day for FY26 Purchase Orders in TeamWorks Settlement Last check run from legacy system Final settlement run in TeamWorks Business Assets Record Asset Depreciation Run journal generate process | All Finance and Procurement Roles | July 10 | July 10
July 2026 (Page 2 of 4)

## Slide 12
Go-Live Calendar: Additional Task Detail
Task / Activity | Impacted Business Area | Date/Timeframe | Final Due Date
FY26 Period 12 Closes in TeamWorks – Final Day to Make Payments For all business areas, Agencies will have full access to TeamWorks modules to perform Period 12 closeout until 7 p.m. on July 10, 2026. July 10 is the final day for any payments or transactions to be made in TeamWorks. The following is a list of activities that must be completed by July 10 in TeamWorks. Manual Journals Enter Manual Journals for FY26 Period 12 Ad-Hoc Payments Enter Ad-hoc payments in GA@WORK Transactional Data Finish and finalize in-scope day-to-day transactions. P-Card Final P-Card statements should be paid | All Finance and Procurement Roles | July 10 | July 10
Provide Outstanding Payments from TeamWorks Provide details (via KiteWorks) of outstanding payments made from TeamWorks that have not cleared the bank as of June 30. | Banking Roles | July 11 – July 15 | July 15
Converted Grants Billing and AR Amounts – Cohort 1 (Agencies part of early close) Agencies to provide the following by July 13: LTD Billed Amount – Cost Reimbursable Journal Load Files for Converted Grants LTD Unbilled Amount – Cost Reimbursable Journal Load Files for Converted Grants Open AR Amount – Billed Cost Reimbursable for Converted Grants | Agency Grants Management Roles | July 13 | July 13
Agencies to confirm July payment in Alight system Agency log into Alight to confirm payment made from TeamWorks on July 9 (Note: SAO will do this for agencies on PYSS) | HR/Accounts Payable Roles | July 15 | July 15
Settle Payroll 3rd Party Deduction Recipient Payments List of which payments are due when to be provided separately | Settlement Roles | July 15 | July 15
Period 998 Closeout (early close agencies) in TeamWorks Early close Agencies complete final Period 998 transactions, reconciliations, approvals, and exception resolutions until 7 p.m. | Finance Roles, AP/AR Roles | July 17 | July 17
TeamWorks Finance Data Available in GA@WORK Open supplier/customer invoices, PO, asset data available in GA@WORK. | Finance Roles, AP/AR Roles | July 24 | July 24
Share Outstanding Checks Information with Banks Provide banks with an updated list of issued checks that have not yet cleared to support reconciliation and positive pay exception handling. Note: this will only apply to certain bank accounts | Banking Roles | July 20 - 31 | July 31
July 2026 (Page 3 of 4)

## Slide 13
Go-Live Calendar: Additional Task Detail
Task / Activity | Impacted Business Area | Date/Timeframe | Final Due Date
Adaptive Soft Go-live Open Adaptive PROD to Validate foundational elements, FY27 Budgets, FY26 balances and load Drivers for next year forecast | Enterprise Budget Managers, Finance Roles | July 28 | July 28
Period 998 Closeout (late close agencies) in TeamWorks Late close agencies complete final Period 998 transactions, reconciliations, approvals, and exception resolutions until 7 p.m. | Finance Roles, AP/AR Roles | July 31 | July 31
Settle Payroll 3rd Party Deduction Recipient Payments List of which payments are due when to be provided separately | Settlement Roles | July 31 | July 31
July 2026 (Page 4 of 4)

## Slide 14
Monday | Tuesday | Wednesday | Thursday | Friday
3 | 4 | 5 | 6 | 7
10 | 11 | 12 | 13 | 14
17 | 18 | 19 | 20 | 21
24 | 25 | 26 | 27 | 28
31 |  |  |  | 
Go-Live Calendar: Finance & Procurement
August 2026
FY26 P11, P12 AND 998 JOURNALS AVAILABLE
FY27 BUDGET VALIDATION
FY27 BUDGET VALIDATION
FY27 BUDGET VALIDATION
FY27 BUDGET VALIDATION
ADAPTIVE PLANNING
GO-LIVE
Grants:
Provide Converted Grants Billing & AR Amounts – Cohort 2
GRANTS: CREATE NEW SPONSOR INVOICES
GRANTS: CREATE NEW SPONSOR INVOICES
GRANTS: CREATE NEW SPONSOR INVOICES
GRANTS: CREATE NEW SPONSOR INVOICES
GRANTS: CREATE NEW SPONSOR INVOICES
GRANTS: SPONSOR BILLING AND RECORDING PAYMENTS (SELECT AGENCIES)
BANKING: REVIEW BALANCE IN ACCOUNT 199999
BANKING: REVIEW BALANCE IN ACCOUNT 199999
BANKING: REVIEW BALANCE IN ACCOUNT 199999
BANKING: REVIEW BALANCE IN ACCOUNT 199999
KEY
Acct. Payable
Supplier Acct.
Adaptive
FDM
Budget
Grants
Banking
Expenses
PRO
General FIN
Bus. Assets
Projects
FY27 BUDGET VALIDATION
GRANTS: SPONSOR BILLING AND RECORDING PAYMENTS (SELECT AGENCIES)
GRANTS: SPONSOR BILLING AND RECORDING PAYMENTS (SELECT AGENCIES)
GRANTS: SPONSOR BILLING AND RECORDING PAYMENTS (SELECT AGENCIES)

## Slide 15
Go-Live Calendar: Additional Task Detail
Task / Activity | Impacted Business Area | Date/Timeframe | Final Due Date
Grants Sponsor Invoices Create New Sponsor Invoices in GA@WORK | Agency Grants Management Roles | July 1 and going forward | --
FY27 Budget Validation Agencies using the Adaptive Planning budget module will need to validate their FY27 budgets. | Budget Officers | August 1 – 31 | August 31
Adaptive Go-live for all agencies | Adaptive Planning/ Budget Offices | August 3 | --
Converted Grants Billing & AR Amounts – Cohort 2 (DCH, DHS, GVRA) Agencies to provide the following by August 5: Provide LTD Billed Amount – Cost Reimbursable Journal Load Files for Converted Grants Provide LTD Unbilled Amount – Cost Reimbursable Journal Load Files for Converted Grants Provide Open AR Amount – Billed Cost Reimbursable for Converted Grants | Agency Grants Management Roles | August 5 | August 5
FY26 P11, P12 and 998 Journals Available TeamWorks FY Period 11, Period 12 and 998 summary journal entries will be available in GA@WORK. | Finance Roles | August 11 | --
Review Balance in Account 199999 Agencies review the balance in account 199999 in GA@WORK as this balance represents the cash balance in TeamWorks that were not identified in the bank balance, outstanding checks and outstanding deposits that are recorded in GA@WORK cash accounts (Accounts 101000/101200). | Banking Roles | August 12 – August 31 | August 31
Sponsor Billing and Payments (select agencies) Start Sponsor Billing and recording payments in GA@WORK (DCH, DHS, GVRA) | Agency Grants Management Roles | August 13 and going forward | --
August 2026