## Slide 1
Monday | Tuesday | Wednesday | Thursday | Friday
 |  |  |  | 1
4 | 5 | 6 | 7 | 8
11 | 12 | 13 | 14 | 15
18 | 19 | 20 | 21 | 22
25 STATE HOLIDAY | 26 | 27 | 28 | 29
May 2026
Security: Agency Security Role Mapping
Security: Agency Security Role Mapping
As of: 05.05.26
Review the activities and dates on this calendar to facilitate the transition from TeamWorks to GA@WORK. Send any questions to nextgen@sao.ga.gov.
Get to Go-Live Calendar: Technical and Security
KEY
Data Conversion/Integrations
Security
Security: ASPs Complete eLearning
Security: Share Sign-In Communications
Security: Share Sign-In Communications
Security: Share Sign-In Communications
Security: Share Sign-In Communications

## Slide 2
Get to Go-Live Calendar: Additional Task Detail
Task / Activity | Roles | Date
Share Sign-In Communications ASPs and Agency POCs should collaborate to update the GA@WORK Sign-ON Communications Template and share it with employees to inform them of how they will access the system at go-live. | Agency ASPs | May 4 – June 30
ASPs Complete eLearning Agency Security Partners should complete their assigned eLearning in Team Georgia Learning by May 18 | Agency ASPs | May 18
Security Role Mapping Agency Security Role Partners map employees to correct security role. Templates are to be submitted by May 29. | Agency ASPs | May 18 – 29
May 2026

## Slide 3
Monday | Tuesday | Wednesday | Thursday | Friday
1 | 2 | 3 | 4 | 5
8 | 9 | 10 | 11 | 12
15 | 16 | 17 | 18 | 19
22 | 23 | 24 | 25 | 26
29 | 30 |  |  | 
Get to Go-Live Calendar: Technical and Security
June 2026
Security: Provision GA@WORK access for Soft Launch Users
Security: Confirm agencies are aware of GA@WORK
Sign-In process
Security: Catch-up Transactions; Test GA@WORK SSO Connection & Onboard End Users to GA@WORK Production Access
Security: Catch-up Transactions; Test GA@WORK SSO Connection & Onboard End Users to GA@WORK Production Access
SOFT LAUNCH
SOFT LAUNCH
Data Conversion: Legacy HCM/Payroll Data Converted to GA@WORK
Data Conversion: Legacy HCM/Payroll Data Converted to GA@WORK
Data Conversion: Catch Up HCM/Payroll Data Converted to GA@WORK
Data Conversion: Finance/Procurement Master Data
Converted to GA@WORK)
Data Conversion: Legacy Journals (All Periods), FY2026 (Period 1-10)
Data Conversion: Legacy Journals (All Periods), FY2026 (Period 1-10)
Integrations: Integration sFTP connectivity testing
Integrations: Integration GA@WORK API connectivity testing
Security: Share Sign-In Communications
Data Conversion: Finance/ Procurement Master Data
Converted to GA@WORK
Security: Share Sign-In Communications
Security: Share Sign-In Communications
Data Conversion: Catch Up HCM/Payroll Data Converted to GA@WORK
Security: Share Sign-In Communications
KEY
Data Conversion/Integrations
Security

## Slide 4
Get to Go-Live Calendar: Additional Task Detail
Task / Activity | Roles | Date
Share Sign-In Communications ASPs and Agency POCs should collaborate to update the GA@WORK Sign-ON Communications Template and share it with employees to inform them of how they will access the system at go-live. | Agency ASPs | May 4 – June 30
TeamWorks HCM/Payroll Data converted to GA@WORK Data taken on May 31 snapshot data is converted to GA@WORK | Data Conversion | June 1 - 11
TeamWorks Finance/ Procurement Master Data Converted to GA@WORK Data taken on June 6 snapshot data is converted to GA@WORK | Data Conversion | June 6 - 13
Confirm Agencies are Aware of Sign-In Process ASPs and Agency POCs to confirm that communications related to their agency’s assign-in process have been shared so that employees are aware of how to sign-in on day one | Security/POCs | June 15
Integration sFTP Connectivity Testing Tests the credentials of SFTP or API endpoints between GA@WORK and the Vendor/Agency System to ensure communications are established appropriately | Integrations | June 15 - 19
Provision GA@WORK Access for Soft Launch Agency ASPs and IDPs work to make sure employees are granted correct access to complete activities for Soft Launch catch-up activities | Security | June 17 - 19
Legacy Journals (All Periods), FY2026 (Period 1-10) Convert legacy system Journals data to GA@WORK | Data Conversion | June 18 - 25
Integration GA@WORK API Connectivity Testing Tests the credentials of GA@WORK API endpoints between GA@WORK and the Vendor/Agency System to ensure communications are established appropriately | Integrations | June 22 - 28
Security Catch Up Transactions Any catch-up transactions related to security role mapping for agencies will take place during the soft launch window | Security | June 22 - 30
Test GA@WORK SSO Connection & Onboard End Users to GA@WORK Production Access Agencies that will utilize SSO in GA@WORK will test the SSO connection to GA@WORK Production Tenant and onboard their users to their agency’s Active Directory | Security | June 22 - 30
GA@WORK Soft Launch On a limited basis, agencies will be granted the ability to make updates in GA@WORK in preparation for go-live. Access will be restricted to only necessary roles. ASPs will be granted access to complete catch-up for Security Role Mapping | ASPs / IdPs | June 22 - 30
Catch Up HCM/Payroll Data Converted to GA@WORK All data from catch up transaction is converted to GA@WORK | Data Conversion | June 26 - 30
June 2026

## Slide 5
Monday | Tuesday | Wednesday | Thursday | Friday
 |  | 1 | 2 | 3 STATE HOLIDAY
6 | 7 | 8 | 9 | 10
13 | 14 | 15 | 16 | 17
20 | 21 | 22 | 23 | 24
27 | 28 | 29 | 30 | 31
Get to Go-Live Calendar: Technical and Security
July 2026
Data Conversion: Semi-Monthly Payroll Confirmed in GA@WORK
Data Conversion: Monthly Payroll Confirmed in GA@WORK
Data Conversion: Finance/Procurement Transactions Data Converted to GA@WORK
Data Conversion: Finance/Procurement Transactions Data Converted to GA@WORK
GO-LIVE!
Security: Users have access to GA@WORK
KEY
Data Conversion/Integrations
Security

## Slide 6
Get to Go-Live Calendar: Additional Task Detail
Task / Activity | Roles/Business Area | Date
GA@WORK Go-Live GA@WORK is open for all end users | All Employees | July 1
Users Sign In to GA@WORK and Complete Business Processes Agency employees are able to sign in to GA@WORK and complete processes in accordance with their assigned security roles | All Employees / ASPs / IdPs | July 1
Semi-Monthly Payroll Confirmed in GA@WORK Semimonthly payroll confirmed in GA@WORK for Pay date of July 15 | Data Conversion | July 9
FIN/PROC Transactions Data converted to GA@WORK Open/In Progress Purchase Orders, Supplier Contracts, Supplier Invoices, Customer Invoices, Assets, LTD Journals, Payroll Costing Allocations | Data Conversion | July 11 - 24
Monthly Payroll Confirmed in GA@WORK Monthly payroll confirmed in GA@WORK for Pay date of July 31 | Data Conversion | July 27
July 2026

## Slide 7
Monday | Tuesday | Wednesday | Thursday | Friday
3 | 4 | 5 | 6 | 7
10 | 11 | 12 | 13 | 14
17 | 18 | 19 | 20 | 21
24 | 25 | 26 | 27 | 28
31 |  |  |  | 
Get to Go-Live Calendar: Technical and Security
August 2026
Data Conversion: Finance/Procurement Journal Transactions Data Converted to GA@WORK
Data Conversion: Finance/Procurement Journal Transactions Data Converted to GA@WORK
KEY
Data Conversion/Integrations
Security

## Slide 8
Get to Go-Live Calendar: Additional Task Detail
Task / Activity | Roles | Date
Finance/Procurement Journal Transactions Data Converted to GA@WORK Manual Journal Transactions and Beginning Balances | Data Conversion | August 1 - 11
August 2026